## Summary
Activity | Owner | Comment | Detail Discussion | Intial Release Date | Review Date | Review-Rework | Signoff | Status % completion
Screen Mockups on Paper | Santosh | Shared with Amol+Das | Started | TBD | 2015-02-03 | TBD | No | 80%
Screen Mockups on WireFrames | Das | Did for LoginPage | Started | 13/3/2015 | 16/03/2015 | TBD | No | 2%
DB design | Swami |  | YTS | 16/3/2015 | 17/03/2015 | TBD | No | 2%
DB content | Swami | Sample data needs to be in DB | YTS
Environment Setup | Vishal/Amol | Team working with Vishal to setup eclipse+LifeRay plugin | Started | TBD | TBD | TBD | No | 10%
Business Flow Diagram | Santosh/Amol | Overview given to team | Started | 14/03/2015 | 16/03/2015 | TBD | No | 50%
Architecture Diagram | Vishal/Swami/Manoj | Need call with swami, manoj, vishal to understand requirement and comeup with Architecture diagram. | YTS | TBD | TBD | TBD | No | 0%
Screen Flows | Santosh/Amol | Explained to team | Started | TBD |  |  |  | 50%
Exploring LifeRay portal | Vishal/Amol/Mahesh |  | Started |  |  |  |  | 2%
Convert Screen Mockups to LifeRay compatible pages | Amol/Mahesh/Vishal |  | Started |  |  |  |  | 1%
POC screen contents | Santosh/Vishal/Swami | Screen Content needs to be decided | YTS |  |  |  |  | 0%
Daily Scrum Meeting ( 10AM IST) | Santosh | Need to send invite to all | YTS |  |  |  |  | 0%
Use GitHub as SourceCode, Document repository | Vishal | Exploring various packages between Private and Public. Public looks good at the moment for POC since Private is chargable. | Started |  |  |  |  | 0%
Client Registrations | Shama/Santosh | Reachout to organizations to be BETA testers, customer. | Started
Leverage AWS capabilities to fit our project | Vishal/Manoj/Amol | Initial video shared with team | Started |  |  |  |  | 2%
IdeaClicks Inc registration | Santosh/Manoj | Can be registered as Propriatory firm in India. Manoj to comeback on US registration. Please feel free to suggest alternate names. | YTS
Site domain name purchase ( IdeaClicks.com) | Santosh/Manoj |  | YTS
Apriori algorithm usage for Data Mining | Santosh/Mahesh | Analytical Engine | YTS
Exploring LifeRay Alloy-UI | Amol |  | Started | 2015-03-16 |  |  | No | 50%
Design login,organization_reg pages with validation | Amol | Validation using alloy-UI | Completed | 2015-03-17 |  |  | No | 80%
Design Admin_Reg,User_Reg pages with validation | Amol | Validation using alloy-UI | Completed | 2015-03-18 |  |  | No | 80%
Design Idea mangement ,Create_campaign pages with validation | Amol | Validation using alloy-UI | Completed | 2015-03-18 | 2015-03-19 | TBD | No | 80%
set up mysql with liferay portal | Amol |  | Completed | 2015-03-19 |  |  | No | 100%
Succesfully saved data on mysql | Amol |  | Completed | 2015-03-19 | 2015-03-20 | TBD |  | 80%
Design Database Tables on paper | Amol/santosh |  | Completed | 2015-03-20 | 2015-03-21 | TBD | No | 90%
Database table created on mysql | Amol |  | Completed | 2015-03-21 | 2015-03-23 | TBD | No | 100%
Explored github | Amol |  | Started | 2015-03-23 |  |  | No | 90%
set up github with eclipse | Amol/Vishal |  | Completed | 2015-03-23 |  |  |  | 100%
Database Script commited on github | Amol |  | Completed | 2015-03-24 | 2015-03-25 | TBD |  | 100%
exploring Junit | Amol |  | Started | 2015-03-25 |  |  | No | 50%
Created project on Junit Testing | Amol |  | Started | 2015-03-27 | 2015-03-30 | TBD | No | 50%
Explored AWS | Amol |  | Started | 2015-03-30 |  |  | No | 60%
AWS Setup with eclipse | Amol/santosh | Don’t know how to setup Amazon EC2 Tomcat V6.0 Cluster in Eclipse | Started | 2015-03-31 | 2015-03-31 | TBD |  | 80%
Successfully saved data in aws RDS database | Amol |  | Started | 2015-03-01 |  |  | No | 10%
Explored Webex | Amol/santosh |  | Completed | 2015-04-02 |  |  |  | 80%
Successfully shared screen on Webex | Amol/santosh |  | Started | 2015-04-02 | 2015-04-02 | TBD |  | 20%
Remaining-How to deploy web pages on AWS? |  |  | Incomplete |  |  |  |  | 0%
Remaining-Captcha Code |  |  | Incomplete |  |  |  |  | 0%
Remaining-UI design |  |  | Incomplete |  |  |  |  | 0%
Resource wise Plan | Activitiy
Vishal | Cloud and webservices POC
Santosh | Screen Mockups
Amol | HTML Prototype
UI/UX (CSS+HTML files) | required
Das | Deployment-LIVE
List of Technology to use | Description
AWS | AmazonWebServices-Cloud
Balsamiq | Screen Flows and mockups
JSP_Servlet | Web page development
MySQL | DB server
?? | App server
TomCat | Web server
JS | Java Script
LifeRay portal | Portal development
GitHub | SourceCode repository
Apriori algorithm | For Analytical Engine
Legends | POC - Proof Of Concept |  | TBD-To Be Decided
YTS-Yet To Start